## Requirement Issue
Sno | CSCI | Raised on Date | REQ ID | Clarification | Issue in CIRD/AC-ICD/CAN-ICD/Others | Developer Response | Raised by | Priority | Query Type | Document Referred | CIRD Phase | Section Referred | Priority | Resolved by | Raised On | Expected Closure | Actual Closure | Status | Remarks | Currently Pending with
1 | OPSW | 2024-06-11 | CDP-SW-SRS-109834 | Requirement specifies "The CDP Operational Software shall transmit following configuration data", but it does not specify over which message the configuration data has to be transmitted. |  | Sangeetha: Updated | Veronica |  | Documentation | SRS 11748 | [7 empty] | OPEN |  | Development
2 | OPSW | 18-4-2024 | CDP-SW-SRS-49153 | Requirement not verifiable. Requirement CDP-SW-SRS-49153 specifies "The CDP Operational software shall process the incoming message, when", but it does not say what prcessing actually means here. |  | Sangeetha: Updated | Veronica |  | Documentation | SRS 11748 | [7 empty] | CLOSED |  | Development
3 | OPSW | 18-4-2024 | CDP-SW-SRS-109857 | Mismatch between SRS and ICD. Requirement specifies Payload/ Signal Name for the message DATE_TIME as "Date_Time", but is different in ICD |  | Sangeetha: Updated | Veronica |  | Documentation | SRS 11748 | [7 empty] | CLOSED |  | Development
4 | OPSW | 18-4-2024 | CDP-SW-SRS-49157 | Requirement not clear. Looks like requirement CDP-SW-SRS-49157 is redundant of CDP-SW-SRS-49156. |  | Sangeetha: Reject. there is difference between the CDP pages | Veronica |  | Documentation | SRS 11748 | [7 empty] | OPEN |  | Development
5 | OPSW | 22-4-2024 | CDP-SW-SRS-49203 CDP-SW-SRS-47669 CDP-SW-SRS-47670 CDP-SW-SRS-47673 CDP-SW-SRS-47677 | In requirement, mentioned figure number is wrong. |  | Sangeetha: Updated | Veronica |  | Documentation | SRS 11748 | [7 empty] | CLOSED |  | Development
6 | OPSW | 23-4-2024 | CDP-SW-SRS-98061 | The below menctioned signals are not available in ICD (Rpt 11594_Rev_F 1)documnet. Switch_Fault_Status PB_PDU_Stop_Fault LED_Panel_Enabled_Fault |  | Sangeetha: Raised clarification. this will be updated in the upcoming phases | Sreenivas |  | Documentation | SRS 11748 | [7 empty] | OPEN |  | Development
7 | CDP SW Main page | 23-4-2024 | CDP-SW-SRS-98113 | Requirement not verifiable.( Few more information needs to be there to check the requirement) The CDP Operational software shall only provide information to the operator. |  | Sangeetha: Raised clarification. | Jyostna |  | Documentation | SRS 11748 | [7 empty] | OPEN |  | Development
8 | CDP SW Main page | 23-4-2024 | All | Entire requiremtims in the section 7.15 all the figure no is worng needs to be updated |  | Sangeetha: Updated | Jyostna |  | Documentation | SRS 11748 | [7 empty] | CLOSED |  | Development
9 | BLSW | 23-4-2024 | CDP-BL-SRS-91321 CDP-BL-SRS-90277 CDP-BL-SRS-90278 | The requirement says the booloader is expected to perform few initialization tasks in a sequence. But how this could be tested needs clarification as no clear output could be seen to verify it. |  |  | Dharshini |  | Documentation | SRS 11748 | [7 empty] | OPEN |  | Development
10 | PLSW | 23-4-2024 | CDP-PLAT-SW-SRS-90417 | The requirement says "The CDP Platform Software shall read the following GPIO pins and validate the configuration..". What will be the output when the GPIO pins are not configured is not mentioned clearly. More clarification on actually how the configuration is being validated will be useful. |  | This req is for detecting the fault in conficuguration , the fault logging related requirements are yet to developed. verifiablity: Its not verifiable at the moment need further discussed and query shall be raised to Ancra Verification of this requirement should be kept on Hold. Reviewer to Raise PR if required. | Dharshini |  | Documentation | SRS 11748 | [7 empty] | OPEN |  | Development
11 | PLSW | 23-4-2024 | CDP-PLAT-SW-SRS-90425 | An UART configuration based requirement - Need clarification on terms "RTS and CTS are available" |  | Sangeetha: Refer Table-4 for Acronym | Dharshini |  | Documentation | SRS 11748 | [7 empty] | CLOSED |  | Development
12 | OPSW | 24-4-2024 | CDP-SW-SRS-49222 CDP-SW-SRS-47669 | Requirement CDP-SW-SRS-49222 tells about "the LCP 4LH or LCP 4RH button on the selected Section" on the Continuous monitoring Page, but the figure in requirement CDP-SW-SRS-47669 does not has the section button for LCP 4LH or LCP 4RH. |  | Sangeetha: Updated | Veronica |  | Documentation | SRS 11748 | [7 empty] | OPEN |  | Development
13 | BLSW | 24-4-2024 | CDP-BL-SRS-91438 | The requirement is certification based, which can not be tested. |  |  | Dharshini |  | Documentation | SRS 11748 | [7 empty] | OPEN |  | Development
14 | BLSW | 24-4-2024 | CDP-BL-SRS-112178 CDP-BL-SRS-112179 | Both the requirement states about the RAM test failure condition. As RAM test failure cannot be recreated, this scenario cannot be tested |  |  | Dharshini |  | Documentation | SRS 11748 | [7 empty] | OPEN |  | Development
15 | BLSW | 24-4-2024 | CDP-BL-SRS-90723 | This requirement also partially speaks about failure of RAM test. "Failure of this test results in CDP entering INVALID mode." The mentioned part of the requirement cannot be tested. |  |  | Dharshini |  | Documentation | SRS 11748 | [7 empty] | OPEN |  | Development
16 | CDP SW Main page | 25-4-2024 | CDP-SW-SRS-49170 | The requirement says "The CDP Operational software shall indicate the Control Panel status through the Control Panel Icons accordingly in correlation with the Figure 15" in the figure there are more components and some indications are there is those needs to tested more information needs to be there on the requirement |  | Sangeetha: Figure number updated | Jyostna |  | Documentation | SRS 11748 | [7 empty] | OPEN |  | Development
17 | CDP SW Main page | 25-4-2024 | CDP-SW-SRS-49169 | The requirement says "The CDP Operational software shall provide the Panel Status symbols as shown in the Figure 14 " in the figure there are more components and some indications are there is those needs to tested more information needs to be there on the requirement |  | Sangeetha: Figure number updated | Jyostna |  | Documentation | SRS 11748 | [7 empty] | OPEN |  | Development
18 | OPSW | 30-4-2024 | CDP-SW-SRS-98071 | The requirement says The CDP Operational Software shall map the faults listed in the table 36 in column "Faults" to the Fault Signal listed in column "Fault Signal" and sets the Fault to True if the Fault Signal is received as 1 or to False otherwise for the Master Control Panel. "Table 36 is saying LCP Faults to signal mapping." |  | Sangeetha: Updated table numbers | Sreenivas |  | Documentation | SRS 11748 | [7 empty] | CLOSED |  | Development
19 | PLSW | 2024-06-05 | CDP-PLAT-SW-SRS-91022 | The output of the requirement is not defined. The requirement seems to be non-verifiable. Also it has been mentioned as HSIT which is not possible |  |  | Dharshini |  | Documentation | SRS 11748 | [7 empty] | OPEN |  | Development
20 | PLSW | 2024-06-05 | CDP-PLAT-SW-SRS-91395 | According to the requirement the output should be "The CDP Platform Software considers the initialization successful and complete." But what is considered the intialization to be complete is not clearly defined. |  |  | Dharshini |  | Documentation | SRS 11748 | [7 empty] | OPEN |  | Development
21 | PLSW | 2024-06-05 | CDP-PLAT-SW-SRS-90414 | The condition mentioned in the requirement (i.e to set “POST_Fail" to True when the pattern of 1 and 0 is not matching) cannot be replicated. Therefore it seems to be non-verfiable |  |  | Dharshini |  | Documentation | SRS 11748 | [7 empty] | OPEN |  | Development
22 | PLSW | 2024-06-05 | CDP-PLAT-SW-SRS-90432 | The output of the requirement is not defined. The requirement seems to be non-verifiable. Also it has been mentioned as HSIT which is not possible |  |  | Dharshini |  | Documentation | SRS 11748 | [7 empty] | OPEN |  | Development
23 | OPSW | 2024-07-05 | CDP-SW-SRS-98120 CDP-SW-SRS-98117 CDP-SW-SRS-49314 | The requirements seems to be partially verifiable. Specifically the mentioned requirement states mapping few variables/Indicators to Signals, which cannot be verified |  | Sangeetha: Rejected. it can be verifiable through HSIT or Analysis. | Dharshini |  | Documentation | SRS 11748 | [7 empty] | OPEN |  | Development
24 | OPSW | 2024-07-05 | CDP-SW-SRS-98173 | The condition specified for LCP "Panel OFF / Disabled" is unclear. Requirement specifies the following condition: (LCP1LH_Panel_Status !=4 OR LCP1LH_Panel_Status !=5 ) The output is always true for this condition and it has no impact. Please clarify. |  | Sangeetha: Raised clarification | Veronica |  | Documentation | SRS 11748 | [7 empty] | OPEN |  | Development
25 | OPSW | 2024-07-05 | CDP-SW-SRS-98116 | To verify whether PDU_X_Faults_Abnormal (not a CAN signal) is true cannot be verified through HSIT, as neither a CAN signal is received as output, nor a change is notable on the screen |  | Sangeetha: Provided CAN ICD reference for PDU Signals | Dharshini |  | Documentation | SRS 11748 | [7 empty] | CLOSED |  | Development
26 | OPSW | 2024-07-05 | CDP-SW-SRS-49132 CDP-SW-SRS-49134 CDP-SW-SRS-49135 CDP-SW-SRS-49136 CDP-SW-SRS-123348 CDP-SW-SRS-123349 CDP-SW-SRS-98127 | The requirements are very generic and high level. Can we take credit by tracing this requirement to all the requirements that verifies the same? |  | Pending Vijay/ Ravi | Veronica |  | Documentation | SRS 11748 | [7 empty] | OPEN |  | Development
27 | OPSW | 2024-07-05 | CDP-SW-SRS-98118 | The input of the requirement is PDU_X_PDU_Health_Status is to be PDU_Healthy. But in the ICD PDU_Health_status has has only 3 states ( Default, Overall Healthy, Not Healthy) and PDU_Healthy is not one among its states |  | Sangeetha: As we discussed Default value is "0". if value is 0 PDU_X_PDU_Health_Status is will be PDU_Healthy | Dharshini |  | Documentation | SRS 11748 | [7 empty] | CLOSED
28 | OPSW | 2024-07-05 | CDP-SW-SRS-98118 | CAN INPUT Data Fault and PDU_X_Data Stale Fault are not CAN signals (not found in ICD). Need clarification on how it must be tested in HSIT |  | Sangeetha: Provided CAN ICD reference. | Dharshini |  | Documentation | SRS 11748 | [7 empty] | CLOSED |  | Development
29 | OPSW | 2024-07-05 | CDP-SW-SRS-109834 | Requirement specifies "The CDP Operational Software shall transmit following configuration data", but it does not specify over which message the configuration data has to be transmitted. MSN and Airport code is not provided in SRS and ICD. |  | Sangeetha: Updated | Veronica |  | Documentation | SRS 11748 | [7 empty] | OPEN |  | Development
30 | OPSW | 2024-07-05 | CDP-SW-SRS-98127 | The reference requirement numbers CDP-SRS-98156, CDP-SRS-49171, CDP-SRS-49172, CDP-SRS-49168, CDP-SRS-98163 specified is wrong. |  | Sangeetha: Updated | Veronica |  | Documentation | SRS 11748 | [7 empty] | CLOSED
31 | OPSW | 2024-07-05 | CDP-SW-SRS-98173 | In Requirement CDP-SW-SRS-98173 it is talking about the can signal Switch_Fault_Status for all the CP eg: OCP_Switch_Fault_Status, ICP_Switch_Fault_Status etc but we coudnt able to see in the ICD document Report No.: 11594 Rev: F |  | Sangeetha: Raised clarification. this will be updated in the upcoming phases | Jyostna |  | Documentation | SRS 11748 | [7 empty] | OPEN |  | Development
32 | OPSW | 2024-08-05 | CDP-SW-SRS-98173 | "In Requirement CDP-SW-SRS-98173 it is talking about the can signal LCP20FTRH_Panel_Status and LCP20FTLH_Panel_Status for LCP but we coudnt able to see in the ICD document Report No.: 11594 Rev: F but in the xml it is LCP4RH_Panel_Status and LCP4LH_Panel_Status. There is a mismatch between SRS and xml. It is same for Can message also in xml it is LCP4LH_Panel_status and LCP4RH_Panel_status " |  | Sangeetha: xml needs to modify. | Jyostna |  | Documentation | SRS 11748 | [7 empty] | CLOSED
33 | OPSW | 2024-08-05 | CDP-SW-SRS-50961 CDP-SW-SRS-125537 | The requirement in CDP-SW-SRS-50961 is repeated in CDP-SW-SRS-125537. Please Clarify. |  | Sangeetha: Modified the reqt. | Veronica |  | Documentation | SRS 11748 | [7 empty] | CLOSED
34 | OPSW | 2024-08-05 | CDP-SW-SRS-125537 | Requirement says "The tolerance needs to be provided at the lower-level documents". Which is the lower level documet. Please Clarify. |  | Sangeetha: Removed the note and raised clarification. | Veronica |  | Documentation | SRS 11748 | [7 empty] | OPEN
35 | OPSW | 2024-09-05 | CDP-SW-SRS-49273 | Requirement says "The CDP Operational Software shall set the JOYSTICK indicator to the state for the Master Control Panel, as mentioned below: AFT MCP_Joystick_AFT is TRUE FWD when when MCP_Joystick_FWD is TRUE IN CMD when MCP_Joystick_IN is TRUE OUT CMD when MCP_Joystick_OUT is TRUE NEUTRAL when MCP_Joystick_NEUTRAL is TRUE INVALID when MCP_Joystick_Fault is TRUE" Could not find any requirement for JOYSTICK indicator, when all above signals are set to FALSE , please clarify. |  | Sangeetha: Raised clarification | Sreenivas |  | Documentation | SRS 11748 | [7 empty] | OPEN |  | Development
36 | OPSW | 2024-09-05 | CDP-SW-SRS-123400 | The requirement is same as CDP-SW-SRS-123401. Clarify whether it is LCP1RH_PB_Zone_Stop or LCP1LH_PB_Zone_Stop . |  | Sangeetha: Modified the reqt. | Harini S P |  | Documentation | SRS 11748 | [7 empty] | CLOSED
37 | OPSW | 2024-10-05 | CDP-SW-SRS-128859 | The signals for message ULD_INFORMATION is missing in ICD |  | Sangeetha: Raised clarification | Veronica |  | Documentation | SRS 11748 | [7 empty] | OPEN
38 | OPSW | 13/5/2024 | CDP-SW-SRS-49290 | The below menctioned signal is not available in ICD (Rpt 11594_Rev_F 1) and SRS documnet. ICP_PDU_Stop. |  | Sangeetha: Raised clarification | Sreenivas |  | Documentation | SRS 11748 | [7 empty] | OPEN
39 | OPSW | 2024-10-05 | CDP-SW-SRS-49298 CDP-SW-SRS-123440 CDP-SW-SRS-49299 CDP-SW-SRS-123441 CDP-SW-SRS-49300 CDP-SW-SRS-123442 | Requirement does not clearly specify, what will be the output if all are FALSE? |  | Sangeetha: Raised clarification | Veronica |  | Documentation | SRS 11748 | [7 empty] | OPEN |  | Development
40 | OPSW | 13/5/2024 | CDP-SW-SRS-98068 | Requirement not clear: The CDP Operational Software shall set the Panel Status indicator to the enumerated value of MCP_Panel_Status for the Master Control Panel as defined in the CAN ICD Rpt 11594. what is the enumerated value of MCP_Panel_Status for MCP in CAN ICD needs to be verify. |  | Sangeetha: As already discussed refer the CAN ICD Signal Description column for Panel status enumaerated values of states for all Control panels and updated Section number for reference | Sreenivas |  | Documentation | SRS 11748 | [7 empty] | CLOSED
41 | OPSW | 13/5/2024 | CDP-SW-SRS-98072 | Requirement not clear: The CDP Operational Software shall set the Mux Current/ Voltage to the enumerated value of MCP_Mux_Current_Voltage for the Master Control Panel as defined in CAN ICD Rpt 11594. what is the enumerated value of MCP_Mux_Current_Voltage for the MCP as defined in CAN ICD Rpt 11594 needs to be verify. |  | Sangeetha: As already discussed refer the CAN ICD Signal Description column for Panel status enumaerated values of states for all Control panels and updated Section number for reference | Sreenivas |  | Documentation | SRS 11748 | [7 empty] | CLOSED
42 | OPSW | 13/5/2024 | CDP-SW-SRS-98074 | Requirement not clear: The CDP Operational Software shall set the Measured Current/ Voltage indicator to MCP_Measured_Current_Voltage for the Master Control Panel. what value need to set and verify for MCP_Measured_Current_Voltage, please clarify |  | Sangeetha: As already discussed refer the CAN ICD Signal Description column for Panel status enumaerated values of states for all Control panels and updated Section number for reference | Sreenivas |  | Documentation | SRS 11748 | [7 empty] | CLOSED
43 | OPSW | 15/5/2024 | CDP-SW-SRS-98068 CDP-SW-SRS-98072 CDP-SW-SRS-98074 | CAN ICD Signal Description column for Panel_Status, Mux_Current_Voltage and Measured_Current_Voltage enumaerated value insted of Default it should be INVALID.Please clarify |  | Sangeetha: Raised clarification | Sreenivas |  | Documentation | SRS 11748 | [7 empty] | OPEN |  | Development
44 | OPSW | 15/5/2024 | CDP-SW-SRS-49140 | "The CDP Operational software shall receive the CARGO_ZONE_ENABLED message computed at CPIOM via CAN bus." can not be verify the CARGO_ZONE_ENABLED messages throug HSIT, please clarify |  | Pending with Mubeen | Sreenivas |  | Documentation | SRS 11748 | [7 empty] | OPEN |  | Development
45 | OPSW | 21/5/2024 | CDP-SW-SRS-49136 | The Requirement says: "The CDP Operational Software shall receive the following messages via CAN bus(A15) and process the messages at the rate mentioned in below Table 10" what is mean by process, please clarify |  | Sangeetha: updated | Sreenivas |  | Documentation | SRS 11748 | [7 empty] | OPEN |  | Development
46 | PLSW | 21/5/2024 | CDP-PLAT-SW-SRS-90418 | Need clarification whether the CDP_SMARC_DDR_Read_Write_Fault and CDP_CAN_Loopback_Fault can be set to true. |  |  | Dharshini |  | Documentation | SRS 11748 | [7 empty] | OPEN |  | Development
47 | PLSW | 21/5/2024 | CDP-PLAT-SW-SRS-109899 CDP-PLAT-SW-SRS-109900 | Need clarification whether the CDP_CAN_Loopback_Fault can be set to true. |  |  | Dharshini |  | Documentation | SRS 11748 | [7 empty] | OPEN |  | Development
48 | PLSW | 21/5/2024 | CDP-PLAT-SW-SRS-109897 CDP-PLAT-SW-SRS-90423 CDP-PLAT-SW-SRS-90432 | The requirements doesn't seem like to be tested in HSIT method |  |  | Dharshini |  | Documentation | SRS 11748 | [7 empty] | OPEN |  | Development
49 | OPSW | 22/5/2024 | CDP-SW-SRS-49134 | "The CDP Operational software shall implement the function identifier field and node identifier field of CAN data frame as specified in CAN-ICD Rpt 11594 refer section - 3.1.4 and 3.1.5 ." as per above requirement , sw implmented the FID and Node ID . As this is part of recieve message need clarification that for recieve message SW should decode the FID and NODE iD from arbitration ID. if SW is implementing FID and Node iD then it should be part of Transmit message . kindly clarify. in above requirement implment means storing FID and node id in SW? |  | Sangeetha: updated | Sreenivas |  | Documentation | SRS 11748 | [7 empty] | OPEN |  | Development
50 | OPSW | 2024-06-10 | CDP-SW-SRS-49287 CDP-SW-SRS-49288 CDP-SW-SRS-49289 CDP-SW-SRS-123437 CDP-SW-SRS-49284 | Requirement says:"indicator to the state for the Master Control Panel, ICP, OCP" For all indicator MCP, ICP OCP did not menction where to verify the status information In CDP,whether System Status or CONTINUOUS MONITORING PAGE, please clarify |  | Sangeetha: Raised clarification | Sreenivas |  | Documentation | SRS 11748 | [7 empty] | OPEN |  | Development
51 | OPSW | 2024-06-11 | CDP-SW-SRS-49289 | The requirement does not specify, to what value the ZONE indicator for ICP will be set to, when both "ICP_PB_Zone_Select_AFT_LED" and "ICP_PB_Zone_Select_FWD_LED" are set to False |  | Sangeetha: Raised clarification | Veronica |  | Technical | SRS 11748 | [7 empty] | OPEN |  | Development
52 | OPSW | 2024-06-11 | CDP-SW-SRS-49293 | The requirement does not specify, to what value the SIDE SELECT indicator for ICP will be set to, when both "ICP_PB_Side_Select_Left_LED " and "ICP_PB_Side_Select_Right_LED" are set to False |  | Sangeetha: Raised clarification | Veronica |  | Technical | SRS 11748 | [7 empty] | OPEN |  | Development
53 | OPSW | 2024-06-13 | CDP-SW-SRS-49278 | The requirement does not specify, to what value the SIDE SELECT indicator for MCP will be set , when BOTH "MCP_PB_Side_Select_Left_LED" AND "MCP_PB_Side_Select_Right_LED"are set to FALSE. |  | Sangeetha: Raised clarification | Sreenivas |  | Technical | SRS 11748
54 | OPSW | 2024-06-13 | CDP-SW-SRS-49274 | The requirement does not specify, to what value the ZONE indicator for MCP will be set , when both "MCP_PB_Zone_Select_AFT_LED" and "MCP_PB_Zone_Select_FWD_LED" are set to FALSE |  | Sangeetha: Raised clarification | Sreenivas |  | Technical | SRS 11748
55 | OPSW | 2024-06-14 | CDP-SW-SRS-49258 | LCP20FTLH_LED_Panel_Enabled_Fault - This signal is not defined neither in ICD nor in XML file. Aso this signal is not found for any other LCP other than LCP20FTLH. |  | Sangeetha: updated | Dharshini |  | Technical | SRS 11748 | [7 empty] | OPEN
56 | OPSW | 2024-06-17 | CDP-SW-SRS-47677 | In Figure 36 representing "CDP Continuous Monitoring Page - CP Status Page - LCP 1, LCP 2, LCP 3" , 2 different figures are given with different Tables each. Please provide clarity on which is the original figure |  | Sangeetha: updated | Dharshini |  | Technical | SRS 11748 | [7 empty] | OPEN
57 | OPSW | 2024-06-18 | CDP-SW-SRS-49144 CDP-SW-SRS-98040 CDP-SW-SRS-49147 CDP-SW-SRS-98055 CDP-SW-SRS-98061 | PB_PDU_Stop this signal is repeated for two messages Panel_cmd,Panel_status,for MCP,ICP,LCP and OCP,20FT LH,20 FT RH, LCP1LH,LCP2LH,LCP3LH,LCP1RH, LCP2RH and LCP3RH. which message we should consider for PB_PDU_Stop signal, please clarify. | SRS 11748 | Pending with Mubeen | Sreenivas |  | Technical | SRS 11748 | [7 empty] | OPEN
58 | OPSW | 2024-06-19 | CDP-SW-SRS-49147 | the following signals For MCP, ICP are set but not used any where PB_Power_On_Off PB_Side_Select_Left PB_Side_Select_Right PB_Zone_Select_AFT PB_Zone_Select_FWD PB_LCP_LH2_1_Enable PB_LCP_LH4_3_Enable PB_LCP_RH2_1_Enable PB_LCP_RH4_3_Enable PB_Dual_Operator PB_20FT PB_Spin the following signals for OCP are set but not used any where PB_Power_On_Off PB_Side_Select_Left PB_Side_Select_Right PB_Zone_Select_AFT PB_Zone_Select_FWD PB_Dual_Operator PB_20FT | SRS 11748 | Sangeetha: Raised clarification | Sreenivas |  | Technical | [8 empty] | OPEN
59 | OPSW | 2024-06-19 | CDP-SW-SRS-98055 | The following signals for LCP1LH,LCP2LH,LCP3LH,LCP1RH,LCP2RH,LCP3RH are set but not used any where PB_Dual_Lane PB_Unlock_Next | SRS 11748 | Sangeetha: Raised clarification | Sreenivas |  | Technical | [8 empty] | OPEN
60 | OPSW | 2024-06-19 | CDP-SW-SRS-98061 | All the CDP signlas are set for LCP4LH and LCP4RH are set but not used any where | SRS 11748 | Sangeetha: Raised clarification | Sreenivas |  | Technical | [8 empty] | OPEN
61 | OPSW | 2024-06-19 | CDP-SW-SRS-98040 | The following signals for LCP1LH,LCP2LH,LCP3LH,LCP1RH,LCP2RH,LCP3RH are set but not used any where PB_Dual_Lane PB_Unlock_Next | SRS 11748 |  | Sreenivas |  | Technical | [8 empty] | OPEN

## ATF Issue
# | CSCI | Raised on Date | REQ ID | Clarification | Issue in CIRD/AC-ICD/CAN-ICD/Others | Developer Response | Raised by | Priority | Query Type | Document Referred | CIRD Phase | Section Referred | Priority | Resolved by | Raised On | Expected Closure | Actual Closure | Status | Remarks | Currently Pending with
1 | CDP APP SW | CP APP SW | NA | Unable to send CAN messages from ATF. Analysis: Issue in eDAT_CANFD_VectorCANFD_ANCRA working.xml | ATF | Fixed | Umashankar |  | Major | Rpt 11748.doc | Phase 6 | NA | High | Sangeetha | 2024-08-05 | 2024-10-05 | 2024-10-05 | CLOSED
2 | CDP APP SW | CP APP SW | NA | Unable to send CAN messages from ATF. Analysis: XML not working (eDAT_CANFD_VectorCANFD_ANCRA working.xml). Template numbers needs to be updated | ATF | Fixed | Umashankar |  | Major | Rpt 11748.doc | Phase 6 | NA | High | Dharshini | 22/5/2024 | 24/5/2024 | 24/5/2024 | CLOSED
3 | CDP APP SW | CP APP SW | NA | In XML file, PB_PDU_Stop Signal is mentioned under 2 different CANmessages (Panel status, Panel cmd) This condition is same for all the LCPs | ATF |  | Dharshini |  |  | ATF XML file | Phase 6 |  |  |  | 17/6/2024 |  |  | OPEN
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49

## Software Issue
Sno | CSCI | Raised on Date | REQ ID | Clarification | Issue in CIRD/AC-ICD/CAN-ICD/Others | Developer Response | Raised by | Priority | Query Type | Document Referred | CIRD Phase | Section Referred | Priority | Resolved by | Raised On | Expected Closure | Actual Closure | Status | Remarks | Currently Pending with | Can Messages used for testing
1 | OPSW | 15/5/2024 | NA | Payload of CAN message coming in reverse order. Software not responding to CAN message transmitted |  |  | Umashankar |  |  | Rpt 11748.doc | Phase 6 |  | High | Mubeen | 15/5/2024 | 17/5/2024 | 17/5/2024 | Closed | Endianess issue resolved | Development
2 | OPSW | 20/5/2024 | NA | Segmentation fault while the application is executed |  |  | Umashankar |  |  | Rpt 11748.doc | Phase 6 |  | High | Mubeen | 20/5/2024 | 21/5/2024 | 24/5/2024 | Closed |  | Development
3 | OPSW | 25/5/2024 | NA | Main Page is not reacting to the CAN messages send. Analysis: Software is receiving the CAN messges sent |  |  | Umashankar |  |  | Rpt 11748.doc | Phase 6 |  | High | Mubeen | 25/5/2024 | 26/5/2024 | 26/5/2024 | Closed |  | Development
4 | OPSW | 28/5/2024 | NA | Segmentation fault while the application is executed |  |  | Umashankar |  |  | Rpt 11748.doc | Phase 6 |  | High | Mubeen | 28/5/2024 |  |  | Closed |  | Development
5 | OPSW | 2024-03-06 | NA | Detailed system status page indicators are not getting updated as per requirement |  |  | Umashankar |  |  | Rpt 11748.doc | Phase 6 |  | High | Mubeen | 2024-03-06 |  |  | Closed |  | Development
6 | OPSW | 2024-10-06 | CDP-SW-SRS-49272 | INVALID when MCP_PB_Power_On_Off_Fault = TRUE is not working Message name : MCP_Panel_cmd and arbitration ID: 173A10F0 and Input Payload : "0000008000000000" |  |  | Sreenivas |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
7 | OPSW | 2024-10-06 | CDP-SW-SRS-49274 | Message name : MCP_Panel_status and arbitration ID:173A60F0 for signals MCP_PB_Zone_Select_AFT_LED = TRUE Input Payload : and MCP_PB_Zone_Select_FWD_LED = TRUE Input Payload: "1000000000000000" . Message name : MCP_Panel_cmd and arbitration ID: 173A10F0 for signals MCP_PB_Zone_Select_FWD_Fault and MCP_PB_Zone_Select_AFT_Fault |  |  | Sreenivas |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
8 | OPSW | 2024-10-06 | CDP-SW-SRS-49273 | IN CMD when MCP_Joystick_IN is TRUE, it is displaying IN insted of IN CMD OUT CMD when MCP_Joystick_OUT is TRUE, it is displaying OUT insted of OUT CMD |  |  | Sreenivas |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
9 | OPSW | 2024-10-06 | CDP-SW-SRS-49275 | Message name : MCP_Panel_status and arbitration ID:173A60F0 for signal MCP_PB_PDU_Stop = TRUE Input Payload: 0000400000000000. |  |  | Sreenivas |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
10 | OPSW | 2024-10-06 | CDP-SW-SRS-49276 | Message name : MCP_Panel_status and arbitration ID:173A60F0 for signal MCP_LED_System_Active = TRUE Input Payload: 8000000000000000 MCP_LED_System_Active = FALSE Input Payload:0000000000000000 |  |  | Sreenivas |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
11 | OPSW | 2024-10-06 | CDP-SW-SRS-49277 | Message name : MCP_Panel_status and arbitration ID:173A60F0 for signal MCP_PB_Spin_LED = TRUE Input Payload: 0000800000000000 Message name : MCP_Panel_cmd and arbitration ID: 173A10F0 for signal MCP_PB_Spin_Fault = TRUE Input Payload: 0000000010000000 |  |  | Sreenivas |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
12 | OPSW | 2024-10-06 | CDP-SW-SRS-49278 | Message name : MCP_Panel_status and arbitration ID:173A60F0 for signals MCP_PB_Side_Select_Left_LED and MCP_PB_Side_Select_Right_LED Message name : MCP_Panel_cmd and arbitration ID: 173A10F0 for signals MCP_PB_Side_Select_Left_Fault and MCP_PB_Side_Select_Right_Fault |  |  | Sreenivas |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
13 | OPSW | 2024-10-06 | CDP-SW-SRS-49279 | Message name : MCP_Panel_status and arbitration ID:173A60F0 for signal MCP_PB_20FT_LED Message name : MCP_Panel_cmd and arbitration ID: 173A10F0 for signal MCP_PB_20FT_Fault |  |  | Sreenivas |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
14 | OPSW | 2024-10-06 | CDP-SW-SRS-49280 | Message name : MCP_Panel_status and arbitration ID:173A60F0 for signal MCP_PB_Dual_Operator_LED Message name : MCP_Panel_cmd and arbitration ID: 173A10F0 for signal MCP_PB_Dual_Operator_Fault |  |  | Sreenivas |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
15 | OPSW | 2024-10-06 | CDP-SW-SRS-49281 | IN when MCP_TGLS_20FT_IN is TRUE it is displaying Enabled insted of IN, OUT and INVALID are not working Message name : MCP_Panel_cmd and arbitration ID: 173A10F0 for signals MCP_TGLS_20FT_OUT,MCP_TGLS_20FT_IN and MCP_TGLS_20FT_Fault |  |  | Sreenivas |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
16 | OPSW | 2024-10-06 | CDP-SW-SRS-49282 | INVALID is working, ACTIVE and INACTIVE are not working Message name : MCP_Panel_status and arbitration ID:173A60F0 for signal MCP_PB_LCP_LH2_1_Enable_BOTTOM_LED Message name : MCP_Panel_cmd and arbitration ID: 173A10F0 for signal MCP_PB_LCP_LH2_1_Enable_Fault |  |  | Sreenivas |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
17 | OPSW | 2024-10-06 | CDP-SW-SRS-123433 | (CP name )message name is not displaying Message name : MCP_Panel_status and arbitration ID:173A60F0 for signal MCP_PB_LCP_LH2_1_Enable_TOP_LED Message name : MCP_Panel_cmd and arbitration ID: 173A10F0 for signal MCP_PB_LCP_LH2_1_Enable_Fault |  |  | Sreenivas |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
18 | OPSW | 2024-10-06 | CDP-SW-SRS-49283 | INVALID is working . ACTIVE and INACTIVE are not working Message name : MCP_Panel_status and arbitration ID:173A60F0 for signal MCP_PB_LCP_LH4_3_Enable_BOTTOM_LED Message name : MCP_Panel_cmd and arbitration ID: 173A10F0 for signal MCP_PB_LCP_LH4_3_Enable_Fault |  |  | Sreenivas |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
19 | OPSW | 2024-10-06 | CDP-SW-SRS-98163 | Due to switch fault status , test script is failing |  |  | Jyostna |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
20 | OPSW | 2024-10-06 | Main page view | It is showing 4RH instead of 20FTRH same needs to be updated for LH |  |  | Jyostna |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
21 | OPSW | 2024-10-06 | CDP-SW-SRS-47660 | Not working |  |  | Jyostna |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
22 | OPSW | 2024-10-06 | CDP-SW-SRS-49166 | Not working ( Main page view related ) |  |  | Jyostna |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
23 | OPSW | 2024-10-06 | CDP-SW-SRS-49167 | Not working ( Main page view related ) |  |  | Jyostna |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
24 | OPSW | 2024-10-06 | CDP-SW-SRS-49168 | Not working ( Main page view related ) |  |  | Jyostna |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
25 | OPSW | 2024-10-06 | CDP-SW-SRS-123434 | (CP name )message name is not displaying Message name : MCP_Panel_status and arbitration ID:173A60F0 for signal MCP_PB_LCP_LH4_3_Enable_TOP_LED Message name : MCP_Panel_cmd and arbitration ID: 173A10F0 for signal MCP_PB_LCP_LH4_3_Enable_Fault |  |  | Sreenivas |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
26 | OPSW | 2024-10-06 | CDP-SW-SRS-49284 | INVALID is working . ACTIVE and INACTIVE are not working Message name : MCP_Panel_status and arbitration ID:173A60F0 for signal MCP_PB_LCP_RH2_1_Enable_BOTTOM_LED Message name : MCP_Panel_cmd and arbitration ID: 173A10F0 for signal MCP_PB_LCP_RH2_1_Enable_Fault |  |  | Sreenivas |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
27 | OPSW | 2024-10-06 | CDP-SW-SRS-123437 | (CP name )message name is not displaying Message name : MCP_Panel_status and arbitration ID:173A60F0 for signal MCP_PB_LCP_RH2_1_Enable_TOP_LED Message name : MCP_Panel_cmd and arbitration ID: 173A10F0 for signal MCP_PB_LCP_RH2_1_Enable_Fault |  |  | Sreenivas |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
28 | OPSW | 2024-10-06 | CDP-SW-SRS-49285 | INVALID is working . ACTIVE and INACTIVE are not working Message name : MCP_Panel_status and arbitration ID:173A60F0 for signal MCP_PB_LCP_RH4_3_Enable_Fault Message name : MCP_Panel_cmd and arbitration ID: 173A10F0 for signal MCP_PB_LCP_RH4_3_Enable_Fault |  |  | Sreenivas |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
29 | OPSW | 2024-10-06 | CDP-SW-SRS-123438 | (CP name )message name is not displaying Message name : MCP_Panel_status and arbitration ID:173A60F0 for signal MCP_PB_LCP_RH4_3_Enable_TOP_LED Message name : MCP_Panel_cmd and arbitration ID: 173A10F0 for signal MCP_PB_LCP_RH4_3_Enable_Fault |  |  | Sreenivas |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
30 | OPSW | 2024-10-06 | CDP-SW-SRS-98068 | Message name : MCP_Panel_cmd and arbitration ID: 173A10F0 for signal MCP_Panel_Status |  |  | Sreenivas |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
31 | OPSW | 2024-10-06 | CDP-SW-SRS-98072 | Message name : MCP_Panel_cmd and arbitration ID: 173A10F0 for signal MCP_Mux_Current_Voltage |  |  | Sreenivas |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
32 | OPSW | 2024-10-06 | CDP-SW-SRS-98074 | Message name : MCP_Panel_cmd and arbitration ID: 173A10F0 for signal MCP_Measured_Current_Voltage |  |  | Sreenivas |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
33 | OPSW | 2024-10-06 | NA | It is showing MCP status insted of ICP status in CONTINUOUS MONITORING PAGE |  |  | Sreenivas |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
34 | OPSW | 2024-10-06 | CDP-SW-SRS-49287 | Message name : ICP_Panel_status and arbitration ID:173A62F0 for signal ICP_PB_On_Off_LED Message name : ICP_Panel_cmd and arbitration ID: 173A12F0 for signal ICP_PB_Power_On_Off_Fault |  |  | Sreenivas |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
35 | OPSW | 2024-10-06 | CDP-SW-SRS-49288 | Message name : ICP_Panel_cmd and arbitration ID: 173A12F0 for signals ICP_Joystick_AFT, ICP_Joystick_FWD,ICP_Joystick_IN,ICP_Joystick_OUT, ICP_Joystick_NEUTRAL and ICP_Joystick_Fault |  |  | Sreenivas |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
36 | OPSW | 2024-10-06 | CDP-SW-SRS-49291 | Message name : ICP_Panel_status and arbitration ID:173A62F0 for signal ICP_LED_System_Active |  |  | Sreenivas |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
37 | OPSW | 2024-10-06 | CDP-SW-SRS-49292 | Message name : ICP_Panel_status and arbitration ID:173A62F0 for signal ICP_PB_Spin_LED Message name : ICP_Panel_cmd and arbitration ID: 173A12F0 for signal ICP_PB_Spin_Fault |  |  | Sreenivas |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
38 | OPSW | 2024-10-06 | CDP-SW-SRS-49294 | Message name : ICP_Panel_status and arbitration ID:173A62F0 for signal ICP_PB_20FT_LED Message name : ICP_Panel_cmd and arbitration ID: 173A12F0 for signal ICP_PB_20FT_Fault |  |  | Sreenivas |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
39 | OPSW | 2024-10-06 | CDP-SW-SRS-49295 | Message name : ICP_Panel_status and arbitration ID:173A62F0 for signal ICP_PB_Dual_Operator_LED Message name : ICP_Panel_cmd and arbitration ID: 173A12F0 for signal ICP_PB_Dual_Operator_Fault |  |  | Sreenivas |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
40 | OPSW | 2024-10-06 | CDP-SW-SRS-49296 | Message name : ICP_Panel_cmd and arbitration ID: 173A12F0 for signal ICP_TGLS_20FT_OUT, ICP_TGLS_20FT_IN and ICP_TGLS_20FT_Fault |  |  | Sreenivas |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
41 | OPSW | 2024-10-06 | CDP-SW-SRS-49297 | Message name : ICP_Panel_status and arbitration ID:173A62F0 for signal ICP_PB_LCP_LH2_1_Enable_BOTTOM_LED Message name : ICP_Panel_cmd and arbitration ID: 173A12F0 for signal ICP_PB_LCP_LH2_1_Enable_Fault |  |  | Sreenivas |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
42 | OPSW | 2024-10-06 | CDP-SW-SRS-123439 | Message name : ICP_Panel_status and arbitration ID:173A62F0 for signal ICP_PB_LCP_LH2_1_Enable_BOTTOM_LED Message name : ICP_Panel_cmd and arbitration ID: 173A12F0 for signal ICP_PB_LCP_LH2_1_Enable_Fault |  |  | Sreenivas |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
43 | OPSW | 2024-10-06 | CDP-SW-SRS-49293 | Message name : ICP_Panel_status and arbitration ID:173A62F0 for signal ICP_PB_Side_Select_Left_LED and ICP_PB_Side_Select_Right_LED Message name : ICP_Panel_cmd and arbitration ID: 173A12F0 for signal ICP_PB_Side_Select_Left_Fault and ICP_PB_Side_Select_Right_Fault |  |  | Sreenivas |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
44 | OPSW | 2024-10-06 | CDP-SW-SRS-49289 | Message name : ICP_Panel_status and arbitration ID:173A62F0 for signal ICP_PB_Zone_Select_AFT_LED and ICP_PB_Zone_Select_FWD_LED Message name : ICP_Panel_cmd and arbitration ID: 173A12F0 for signal ICP_PB_Zone_Select_AFT_Fault and ICP_PB_Zone_Select_FWD_Fault |  |  | Sreenivas |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
45 | OPSW | 2024-10-06 | CDP-SW-SRS-49226 | Not working in Continuous Monitoring page |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
46 | OPSW | 2024-10-06 | CDP-SW-SRS-49227 | Not Working in both Continuous Monitoring and Detailed system status page |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
47 | OPSW | 2024-10-06 | CDP-SW-SRS-49228 | Not working in Continuous Monitoring page |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
48 | OPSW | 2024-10-06 | CDP-SW-SRS-49230 | Detailed System page - Invalid is not working. Other states working Continous Monitoring page - Not working completely |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
49 | OPSW | 2024-10-06 | CDP-SW-SRS-49231 | Detailed System page - Invalid is not working. Other states working Continous Monitoring page - Not working completely |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
50 | OPSW | 2024-10-06 | CDP-SW-SRS-123400 | Not working, There is no Zone stop parameter displayed in both Continuous Monitoring page and Detailed system status page |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
51 | OPSW | 2024-10-06 | CDP-SW-SRS-49232 | Not Working in both Continuous Monitoring and Detailed system status page |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
52 | OPSW | 2024-10-06 | CDP-SW-SRS-49233 | Not Working in both Continuous Monitoring and Detailed system status page |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
53 | OPSW | 2024-10-06 | CDP-SW-SRS-49234 | Not Working in both Continuous Monitoring and Detailed system status page |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
54 | OPSW | 2024-10-06 | CDP-SW-SRS-49235 | Not Working in both Continuous Monitoring and Detailed system status page |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
55 | OPSW | 2024-10-06 | CDP-SW-SRS-49236 | Not Working in both Continuous Monitoring and Detailed system status page |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
56 | OPSW | 2024-10-06 | CDP-SW-SRS-123401 | Not working, There is no Zone stop parameter displayed in both Continuous Monitoring page and Detailed system status page |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
57 | OPSW | 2024-10-06 | CDP-SW-SRS-49237 | Detailed System page - Not working, The requirement is for 2LH, but it was reflecting in 1RH Continous Monitoring page - Not working completely |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
58 | OPSW | 2024-10-06 | CDP-SW-SRS-49238 | Not Working in both Continuous Monitoring and Detailed system status page |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
59 | OPSW | 2024-10-06 | CDP-SW-SRS-49239 | Detailed System page - Not working, The requirement is for 2LH, but it was reflecting in 1RH Continous Monitoring page - Not working completely |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
60 | OPSW | 2024-10-06 | CDP-SW-SRS-49240 | Detailed System page - Not working, The requirement is for 2LH, but it was reflecting in 1RH. For Invalid, no changes Continous Monitoring page - Not working completely |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
61 | OPSW | 2024-10-06 | CDP-SW-SRS-49241 | Detailed System page - Not working, The requirement is for 2LH, but it was reflecting in 1RH. For Invalid, no changes Continous Monitoring page - Not working completely |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
62 | OPSW | 2024-10-06 | CDP-SW-SRS-49242 | Detailed System page - Not working, The requirement is for 2RH, but it was reflecting in 3RH Continous Monitoring page - Not working completely |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
63 | OPSW | 2024-10-06 | CDP-SW-SRS-123403 | Not working, There is no Zone stop parameter displayed in both Continuous Monitoring page and Detailed system status page |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
64 | OPSW | 2024-10-06 | CDP-SW-SRS-49243 | Not Working in both Continuous Monitoring and Detailed system status page |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
65 | OPSW | 2024-10-06 | CDP-SW-SRS-49244 | Detailed System page - Not working, The requirement is for 2RH, but it was reflecting in 3RH Continous Monitoring page - Not working completely |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
66 | OPSW | 2024-10-06 | CDP-SW-SRS-49245 | Detailed System page - Not working, The requirement is for 2RH, but it was reflecting in 3RH. For Invalid, no changes Continous Monitoring page - Not working completely |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
67 | OPSW | 2024-10-06 | CDP-SW-SRS-49246 | Detailed System page - Not working, The requirement is for 2RH, but it was reflecting in 3RH. For Invalid, no changes Continous Monitoring page - Not working completely |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
68 | OPSW | 2024-10-06 | CDP-SW-SRS-123406 | Not working, There is no Zone stop parameter displayed in both Continuous Monitoring page and Detailed system status page |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
69 | OPSW | 2024-10-06 | CDP-SW-SRS-49247 | Detailed System page - Not working, The requirement is for 3LH, but it was reflecting in 2LH Continous Monitoring page - Not working completely |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
70 | OPSW | 2024-10-06 | CDP-SW-SRS-49248 | Not Working in both Continuous Monitoring and Detailed system status page |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
71 | OPSW | 2024-10-06 | CDP-SW-SRS-49249 | Detailed System page - Not working, The requirement is for 3LH, but it was reflecting in 2LH Continous Monitoring page - Not working completely |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
72 | OPSW | 2024-10-06 | CDP-SW-SRS-49250 | Detailed System page - Not working, The requirement is for 3LH, but it was reflecting in 2LH. For Invalid, no changes Continous Monitoring page - Not working completely |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
73 | OPSW | 2024-10-06 | CDP-SW-SRS-49251 | Detailed System page - Not working, The requirement is for 3LH, but it was reflecting in 2LH. For Invalid, no changes Continous Monitoring page - Not working completely |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
74 | OPSW | 2024-10-06 | CDP-SW-SRS-123408 | Not working, There is no Zone stop parameter displayed in both Continuous Monitoring page and Detailed system status page |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
75 | OPSW | 2024-11-06 | CDP-SW-SRS-98022 | Panel status in LCP is blank in both Continuous Monitoring page and Detailed system status page for any enumerated input value. |  |  | Harini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
76 | OPSW | 2024-11-06 | CDP-SW-SRS-98038 | Mux current voltage is blank in Continuouse Monitoring page for the input |  |  | Harini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
77 | OPSW | 2024-11-06 | CDP-SW-SRS-98047 | Measured current voltage is blank in Continuouse Monitoring page for the input |  |  | Harini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
78 | OPSW | 2024-12-06 | ID:CDP-SW-SRS-49298 | Not Working in both Continuous Monitoring and Detailed system status page |  |  | Jyostna |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
79 | OPSW | 2024-12-06 | ID:CDP-SW-SRS-123440 | Not Working in both Continuous Monitoring and Detailed system status page |  |  | Jyostna |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
80 | OPSW | 2024-12-06 | ID:CDP-SW-SRS-49299 | Not Working in both Continuous Monitoring and Detailed system status page |  |  | Jyostna |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
81 | OPSW | 2024-12-06 | ID:CDP-SW-SRS-123441 | Not Working in both Continuous Monitoring and Detailed system status page |  |  | Jyostna |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
82 | OPSW | 2024-12-06 | ID:CDP-SW-SRS-49300 | Not Working in both Continuous Monitoring and Detailed system status page |  |  | Jyostna |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
83 | OPSW | 2024-12-06 | ID:CDP-SW-SRS-123442 | Not Working in both Continuous Monitoring and Detailed system status page |  |  | Jyostna |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
84 | OPSW | 2024-12-06 | ID:CDP-SW-SRS-98088 | Not Working in both Continuous Monitoring and Detailed system status page |  |  | Jyostna |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
85 | OPSW | 2024-12-06 | ID:CDP-SW-SRS-98089 | Not Working in both Continuous Monitoring and Detailed system status page |  |  | Jyostna |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
86 | OPSW | 2024-12-06 | ID:CDP-SW-SRS-98094 | Not Working in both Continuous Monitoring and Detailed system status page |  |  | Jyostna |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
87 | OPSW | 2024-12-06 | CDP-SW-SRS-49302 | Invalid is not working for the panel indicator ON /OFF is working |  |  | Jyostna |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
88 | OPSW | 2024-12-06 | CDP-SW-SRS-49304 | Not Working in both Continuous Monitoring and Detailed system status page |  |  | Jyostna |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
89 | OPSW | 2024-12-06 | CDP-SW-SRS-49305 | Not Working in both Continuous Monitoring and Detailed system status page |  |  | Jyostna |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
90 | OPSW | 2024-12-06 | CDP-SW-SRS-49306 | Invalid is not working for the panel indicator ON /OFF is working |  |  | Jyostna |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
91 | OPSW | 2024-12-06 | CDP-SW-SRS-49307 | INVALID and ENABLED is not working DISABLED is working |  |  | Jyostna |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
92 | OPSW | 2024-12-06 | CDP-SW-SRS-49309 | Not Working in both Continuous Monitoring and Detailed system status page |  |  | Jyostna |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
93 | OPSW | 2024-12-06 | CDP-SW-SRS-49310 | Not Working in both Continuous Monitoring and Detailed system status page |  |  | Jyostna |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
94 | OPSW | 2024-12-06 | CDP-SW-SRS-49252 | Detailed System page - Not working, The requirement is for 3RH, but it was reflecting in 4LH. For Invalid, no changes Continous Monitoring page - Not working completely |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
95 | OPSW | 2024-12-06 | CDP-SW-SRS-49253 | Not Working in both Continuous Monitoring and Detailed system status page |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
96 | OPSW | 2024-12-06 | CDP-SW-SRS-49254 | Detailed System page - Not working, The requirement is for 3RH, but it was reflecting in 4LH Continous Monitoring page - Not working completely |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
97 | OPSW | 2024-12-06 | CDP-SW-SRS-49255 | Detailed System page - Not working, The requirement is for 3RH, but it was reflecting in 4LH. For Invalid, no changes Continous Monitoring page - Not working completely |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
98 | OPSW | 2024-12-06 | CDP-SW-SRS-49256 | Detailed System page - Not working, The requirement is for 3RH, but it was reflecting in 4LH. For Invalid, no changes Continous Monitoring page - Not working completely |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
99 | OPSW | 2024-12-06 | CDP-SW-SRS-123411 | Not working, There is no Zone stop parameter displayed in both Continuous Monitoring page and Detailed system status page |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
100 | OPSW | 2024-12-06 | CDP-SW-SRS-49257 | Detailed System page - Not working, The requirement is for 4LH, but it was reflecting in 2RH. For Invalid, no changes Continous Monitoring page - Not working completely |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
101 | OPSW | 2024-12-06 | CDP-SW-SRS-49258 | Not Working in both Continuous Monitoring and Detailed system status page |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
102 | OPSW | 2024-12-06 | CDP-SW-SRS-49259 | Detailed System page - Not working, Its always reflecting as False (Instead of Left/Right) Continous Monitoring page - Not working completely |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
103 | OPSW | 2024-12-06 | CDP-SW-SRS-49260 | Detailed System page - Not working, The requirement is for 4LH, but it was reflecting in 2RH. Continous Monitoring page - Not working completely |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
104 | OPSW | 2024-12-06 | CDP-SW-SRS-49261 | Detailed System page - Not working, The requirement is for 4LH, but it was reflecting in 2RH. Continous Monitoring page - Not working completely |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
105 | OPSW | 2024-12-06 | CDP-SW-SRS-49262 | Detailed System page - Not working, Always displayed as DISABLED (In 2RH, instaed of 4LH) Continous Monitoring page - Not working completely |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
106 | OPSW | 2024-12-06 | CDP-SW-SRS-49263 | Detailed System page - Not working, Always displayed as INVALID (In 2RH, instaed of 4LH) Continous Monitoring page - Not working completely |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
107 | OPSW | 2024-12-06 | CDP-SW-SRS-123427 | Not working, There is no Zone stop parameter displayed in both Continuous Monitoring page and Detailed system status page |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
108 | OPSW | 2024-12-06 | CDP-SW-SRS-49264 | Detailed System page - Not working, as expected it was reflected under 4RH column. But Invalid condition is not working Continous Monitoring page - Not working completely |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
109 | OPSW | 2024-12-06 | CDP-SW-SRS-49265 | Not Working in both Continuous Monitoring and Detailed system status page |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
110 | OPSW | 2024-12-06 | CDP-SW-SRS-49266 | Detailed System page - Not working, Its always reflecting as False (Instead of Left/Right) Continous Monitoring page - Not working completely |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
111 | OPSW | 2024-12-06 | CDP-SW-SRS-49267 | Detailed System page - Not working Continous Monitoring page - Not working completely |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
112 | OPSW | 2024-12-06 | CDP-SW-SRS-49268 | Continous Monitoring page - Not working completely |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
113 | OPSW | 2024-12-06 | CDP-SW-SRS-49269 | Detailed System page - Not working, Always displayed as DISABLED Continous Monitoring page - Not working completely |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
114 | OPSW | 2024-12-06 | CDP-SW-SRS-49270 | Detailed System page - Not working, Always displayed as INVALID Continous Monitoring page - Not working completely |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Closed |  | Development
115 | OPSW | 2024-12-06 | CDP-SW-SRS-123428 | Not working, There is no Zone stop parameter displayed in both Continuous Monitoring page and Detailed system status page |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
116 | OPSW | 13/6/24 | ID:CDP-SW-SRS-98103 | Panel Status indicator of OCP_Panel_Status does not change its status as per the requirement for all the inputs. |  |  | Harini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
117 | OPSW | 13/6/24 | ID:CDP-SW-SRS-98101 | Measured Current/ Voltage of OCP_Measured_Current_Voltage gives the following values: I/p O/p 20 5120 1 256 16383 65343 32765 64895 |  |  | Harini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
118 | OPSW | 17/6/2024 | ID:CDP-SW-SRS-98062 | LCP1LH : Input Payload = 0, Arbitration ID = 173A10F8 The following Faults were not present in the page: LCP1LH Push Button-Zone Stop Fault LCP 1LH Operational Software CRC Fault LCP 1LH NVM Checksum Fault LCP 1LH NVM Integrity Check Fault LCP1RH, LCP2LH, LCP2RH, LCP3LH, LCP3RH, LCP20FTLH, LCP20FTRH : Input Payload = 0, Arbitration ID = 173A12F4, 173A10FC, 173A12F8, 173A1100, 173A12FC, 173A1104, 173A1300 There were no changes in the following faults: LCP1LH Toggle Switch-Drive Fault LCP1LH Push Button-Dual Lane Fault LCP1LH Push Button-Unlock Next Fault LCP1LH Push Button-Lamp Test Fault The following Faults were not present in the respective pages: LCP1LH Push Button-Zone Stop Fault LCP 1LH Operational Software CRC Fault LCP 1LH NVM Checksum Fault LCP 1LH NVM Integrity Check Fault |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
119 | OPSW | 17/6/2024 | ID:CDP-SW-SRS-98110 | Input Payload = 0, Arbitration ID = 173A10F4 There were no changes in the following faults: OCP Operational Software CRC Fault OCP NVM Checksum Fault OCP NVM Integrity Check Fault |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
120 | OPSW | 18/6/2024 | CDP-SW-SRS-98116 | PDUL01 No change in PDU General status indicator. By default it displays "xxxxxxx" Sample PayLoad while setting PDUL01_HVDC_Over_Voltage_Fault to 1: Message Name = PDUL01_Status_msg_1 Arbitration ID = 173A2004 Input PayLoad = 00 00 00 00 40 00 00 00 |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
121 | OPSW | 18/6/2024 | CDP-SW-SRS-98118 | PDUL01 No change in PDU General status indicator. By default it displays "xxxxxxx" Sample PayLoad while setting PDUL01_PDU_Health_Status = 1 and PDUL01_PDU_State = 4: Message Name = PDUL01_Status_msg_1 Arbitration ID = 173A2004 Input PayLoad = 10 04 00 00 00 00 00 00 |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
122 | OPSW | 18/6/2024 | CDP-SW-SRS-123443 | PDUL01 No change in PDU Hold Status. By default it displays "Hold" Sample PayLoad while Setting PDUL01_PDU_State is set to 3: Message Name = PDUL01_Status_msg_1 Arbitration ID = 173A2004 Input PayLoad = 00 03 00 00 00 00 00 00 |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
123 | OPSW | 18/6/2024 | CDP-SW-SRS-49326 | PDUL01 No change in PDU Type indicator. By default it displays "xxxxxxx" Sample PayLoad while Setting PDUL01_PDU_Type is set to 3: Message Name = PDUL01_Status_msg_1 Arbitration ID = 173A2004 Input PayLoad = C0 00 00 00 00 00 00 00 |  |  | Dharshini |  |  | Rpt 11748.doc |  |  | High |  |  |  |  | Open |  | Development
124 | OPSW | 20/6/2024 | CDP-SW-SRS-49303 | (CP name )"SIDE SELECT"message name is not displaying in Continuous Monitoring page Message name = OCP_Panel_status Arbitration ID: 173A60F4 Input PayLoad = 1000000000000000. Message name = OCP_Panel_cmd Arbitation ID

## Summary
Requirement Issue | Count
Total | 61
CODE | 0
SRS | 61
CIRD | 0
Requirement Issue Status | Count
TOTAL | 61
OPEN | 45
CLOSED | 16
AFT Issue | Count
Total | 3
CODE | 0
SRS | 3
CIRD | 0
Requirement Issue Status | Count
TOTAL | 3
OPEN | 1
CLOSED | 2
Software Issue | Count
Total | 124
CODE | 124
SRS | 0
CIRD | 0
Software Issue Status | Count
TOTAL | 124
OPEN | 70
CLOSED | 53